## Slide 1
COMMISSIONING & HANDING OVER PROTOCOL FOR RURAL WATER SUPPLY SCHEMES

## Slide 2
Executive Overview: A Four-Phase Validation Framework
Structured Timeline
The commissioning protocol operates within 2-3 months timeframe, establishing a predictable implementation schedule that bridges construction completion and operational service delivery. This duration encompasses all validation activities necessary to ensure comprehensive system readiness.
Sequential Approach
The protocol employs a phased methodology where each stage builds upon previous outcomes, creating a cumulative validation framework that ensures nothing is overlooked.
Phase 1: Pre-Commissioning
Documentation establishes baseline accountability through as-built drawings, design compliance verification, and comprehensive defect assessment
Phase 2: System Testing
Technical validation confirms performance through pressure testing, water quality analysis, and equipment verification under load conditions
Phase 3: Trial Operations
Real-world functionality validation with continuous monitoring, community integration, and stakeholder engagement throughout the process
Phase 4: Final Documentation
Compliance assurance and knowledge transfer through comprehensive reports, training materials, and regulatory certifications

## Slide 3
Phase 1: Pre-Commissioning Documentation & Verification
1. As-Built Drawings Finalization
1
Accountability through documentation: All deviations from original design specifications must be systematically documented with comprehensive coverage spanning intake systems, pumping stations, pipelines, storage tanks, treatment units, and distribution networks.
Digital asset mapping with geo-tagging integrates with PM Gati Shakti platform
Creates centralized national infrastructure records
Infrastructure maps prominently displayed in villages for transparency
2. Design Compliance Inspection
Technical validation against standards: Independent technical personnel verify all infrastructure components against approved design specifications and BIS standards. This systematic assessment by external parties ensures objective validation and prevents conflicts of interest where contractors verify their own work.
3. Component-Wise Verification
Granular quality assessment: Detailed inspection of pumps, valves, storage tanks, treatment units, metres, electrical panels, and control systems ensures installation completeness and workmanship quality across all infrastructure categories.
4. Visual Defect Assessment
Prevention of failure points: Systematic inspection for defects, leaks, incomplete installations, rusting, damages, and misalignments creates a defect register with documented remedial actions. This preventive approach addresses visible issues before they escalate into operational failures.

## Slide 4
Phase 2A: System Testing & Technical Validation
Hydrostatic Pressure Testing
Pipeline Structural Integrity
Pressurisation to design specifications validates pipeline joint soundness and structural capacity. Comprehensive documentation includes pressure readings, test duration, identified defects, and corrective actions taken.
Low-pressure systems (≤10 bar): Test pressure equals 1.5 times operating pressure
High-pressure systems (>10 bar): Test pressure equals operating pressure plus 5 bar
Sectional testing approaches accommodate large multi-village schemes
01
Tap Connection Leak Testing
Systematic inspection of all household, community, and institutional tap connections ensures leak-free delivery and proper fitting installation—validating that the final-mile infrastructure functions reliably.
02
Flushing and Disinfection
Systematic water circulation removes construction debris, sediments, and contaminants. Chlorination using approved procedures (0.2-0.5 mg/L concentration) complies with CPHEEO manuals and WHO guidelines.
03
Flow and Capacity Testing
Verification that all distribution points deliver 55 LPCD at minimum 7 metres head pressure validates that the scheme meets national service standards under peak demand scenarios.

## Slide 5
Phase 2B: Comprehensive Quality & Equipment Validation
Chemical Parameters
pH, turbidity, fluoride, arsenic, iron, nitrate, and regional contaminants tested at source, treatment plant, distribution points, and household taps
Bacteriological Analysis
E. coli and total coliform testing with zero tolerance threshold ensuring potable water safety per BIS 10500:2012 standards
Physical Assessment
Colour, odour, and taste evaluation ensuring water palatability and community acceptance of the supply
Laboratory Accreditation
ISO/IEC 17025 accredited laboratory analysis ensures credible results and regulatory compliance assurance
Residual Chlorine Level Validation
Multiple distribution point and tail-end household measurements verify that minimum 0.2 ppm chlorine exists at network extremities whilst remaining below 0.5 mg/L maximum to maintain water palatability.
This ensures disinfection protection reaches all beneficiaries without creating taste concerns that discourage system utilization.
Pumps and motors undergo voltage, current, vibration, alignment, and noise verification. Valves and control devices tested under actual load conditions.
Electrical & Mechanical Systems Testing
Sensor accuracy, communication reliability, remote monitoring functionality, and cybersecurity verification prevent equipment failures during extended operation.
SCADA & Automation Validation
Flow meters, pressure gauges, chlorine analyzers, and sensors verified against certified standards ensuring ongoing monitoring accuracy.
Instrument Calibration

## Slide 6
Phase 3: Operational Validation & Community Integration
Continuous Trial Operation
Minimum 7-14 days of continuous operation under actual demand conditions provides extended performance evidence. Round-the-clock monitoring of water flow, pressure levels, water quality, and energy consumption validates system stability and consistency under varying scenarios and peak demand conditions.
Issue Identification & Corrective Action
Systematic documentation captures pressure drops, pump failures, water quality deviations, control system malfunctions, and service interruptions. Root cause analysis prevents minor issues from developing into major failures during subsequent years of operation.
Joint Inspection with Stakeholders
Collaborative transect walks involving engineers, Gram Panchayat representatives, VWSC officials, and community members create transparent validation processes. Formal stakeholder sign-off demonstrates that diverse stakeholders have validated system readiness.
Community Awareness & Behaviour Change
Education initiatives address chlorine concerns through targeted messaging. Capacity building for water management committees ensures local teams understand system operation and maintenance. Coordination with ASHA workers, school programmes, and self-help groups creates multi-channel awareness.
Transparent Accountability: This transparency builds community confidence and ownership whilst ensuring that awareness translates into appropriate system utilisation and protection for long-term sustainability.

## Slide 7
Phase 4: Compliance & Documentation Requirements
Comprehensive Commissioning Report:
Documents testing protocols, results analysis, identified issues, corrective actions, and recommendations. Executive summaries make findings accessible to non-technical stakeholders. Technical appendices with test data, calibration certificates, water quality reports, and photographs create an authoritative institutional record.
Operation Manuals & Training Documentation:
User manuals in local languages with visual aids enable community understanding. Troubleshooting guides systematically diagnose common problems. Maintenance schedules specify routine inspections, component replacement intervals, and preventive measures.
Regulatory Compliance Certification:
Water quality certificates validate BIS 10500:2012 compliance. Pressure test reports verify structural integrity. Electrical safety certificates confirm code compliance. Equipment certifications verify component specifications, creating comprehensive institutional accountability.
Digital Infrastructure Integration
Long-term monitoring and analytics capabilities transform rural water schemes from reactive to proactive management models.
RPWSS module integration: Unique scheme identifiers enable nationwide performance tracking
Geo-tagged asset mapping: Enables targeted maintenance and monitoring
PM Gati Shakti platform: Coordinates schemes within national infrastructure frameworks
JJM WQMIS integration: Centralised water quality monitoring with automated alerts
Real-time monitoring: Enables predictive analytics and data-driven management
IoT integration: Advanced monitoring and predictive maintenance scheduling
"Digital integration enables the transformation from problem-based reactive management to prediction-based proactive management across thousands of rural water schemes nationwide."

## Slide 8
HANDING OVER PROTOCOL FOR RURAL PIPED WATER SUPPLY SCHEMES (RPWSS)
OBJECTIVE: To facilitate smooth, transparent, and sustainable transfer of Rural Piped Water Supply Schemes (RPWSS) from implementing agencies to GPs/VWSCs.
Key Goals:
Systematically transfer assets and financial records to community institutions per JJM guidelines.
Establish mechanisms for effective O&M of in-village infrastructure.
Ensure sustainable service continuity through evidence-based monitoring.
Facilitate a time-bound transition of operations to GPs/VWSCs.
Foster local control and a sense of ownership over water systems.
Build institutional capacity and stewardship through structured support

## Slide 9
Infrastructure Transfer
Handover of water supply systems from implementing agencies to legally constituted community institutions (GPs/VWSCs) according to JJM implementation timelines.
Operational Capacity
GP and VWSC capability to independently manage operation and maintenance activities whilst adhering to defined technical standards and performance benchmarks.
Community Monitoring
Established mechanisms enabling regular assessment and reporting of service continuity, water quality parameters, and physical asset condition by community members.
Institutional Engagement
Sustained collaboration between community water utilities and government agencies for technical backstopping, regulatory compliance, and continuous performance improvement.
Community Participation
Enhanced awareness and active involvement in water supply system management, resulting in improved sustainability and reduced infrastructure deterioration rates.
Financial Viability
Documented reduction in water losses, improved revenue collection efficiency, and demonstrated financial sustainability of water supply schemes at community level.
Expected outcomes

## Slide 10
PREREQUISITES FOR HANDOVER
After completion of the scheme and successful trial run, the following conditions must be met:
Har Ghar Jal Declaration
Official declaration of the village achieving 100% household tap connections
Full Functionality
Entire scheme operational from source to households with adequate pressure and flow
Quality Compliance
Adherence to all quality and safety standards as per JJM guidelines
VWSC Readiness
Completion of O&M training and operational preparedness of Village Committee
1
2
4
3

## Slide 11
CATEGORIES OF READINESS
Completion of Works
1
Functional scheme with leak-free pipelines and working connections
Water quality clearance
2
Laboratory testing and quality certification completed
Operational and Capacity Readiness
3
comprehensive training programs for personnel (NJM etc) with emergency response Protocol, SOP in place
Institutional Framework Establishment
constitution and registration of VWSC and leadership structure with defined roles and responsibilities
5
Community Awareness
Village orientation and joint walkthrough conducted, As-built drawings shared
6
Financial Readiness
Bank account opened with user charge collection system
7
4
Technical Assessment
Complete asset inventory and documentation prepared

## Slide 12
ESSENTIAL DOCUMENTS FOR HANDOVER
1
2
3
4
5
Asset Register & Inventory
Complete listing of all infrastructure components, equipment, and materials with specifications and locations
As-Built Drawings
Detailed technical drawings showing actual construction as completed, including pipeline routes and connections
Maintenance Schedule
Comprehensive preventive and routine maintenance calendar with procedures and checklists
O&M Records & Registers
Standardized formats for daily operations, complaint tracking, and maintenance activity documentation
Water Quality Monitoring Records
Historical testing data, quality parameters, and protocols for ongoing water safety surveillance

## Slide 13
JAL ARPAN DIWAS – A CELEBRATION OF OWNERSHIP
'Jal Arpan’ means offering a pot of water from the source by elders. This ceremonial day marks the official transfer of the Rural Piped Water Supply Scheme to the Gram Panchayat and Village Water & Sanitation Committee.
Purpose of the Ceremony:
Formalise community ownership and stewardship
Celebrate the transfer of trust and accountability
Ensure transparency in document handover and role assignment
Recognise collective efforts in achieving Har Ghar Jal

## Slide 14
SUMMARY OF HANDOVER PRINCIPLES
Before Handover
Complete all civil works, train O&M staff, prepare comprehensive documentation, conduct technical assessments, and ensure VWSC is fully functional
At Handover
Conduct Gram Sabha for community approval, MoU signed by authorized representatives, celebrate Jal Arpan Diwas with Community pledge etc
After Handover
Continue regular monitoring visits, provide ongoing training support, ensure timely technical assistance, and track performance indicators

## Slide 15
ACTIVITY FLOW FOR JAL ARPAN DIWAS
1
Workshop Orientation
Sensitisation of GP members and VWSC on roles, responsibilities, and O&M procedures
2
Jal Bandhan Yatra
Transect walk through the scheme infrastructure with community participation
3
Technical Assessment
Joint inspection and sharing of asset inventory with local stakeholders
Self-assessment Matrix
Focus Group Discussion with GP/ VWSC to facilitate filling up Self-assessment Matrix
5
Financial Planning
Opening of VWSC bank account and discussion on user charges and revenue collection
6
Special Gram Sabha
To discuss and accept the process of handing over the water supply assets to the community.
Jal Arpan Diwas
Formal handover ceremony with documentation, MoU signing, and community festivities
Capacity Building
Support in Institutional Strengthening & Capacity Building of VWSC/ GP for O&M from DTU/ PHED
4
7
8

## Slide 16
ACTIVITIES ON JAL ARPAN DIWAS
Jal Bandhan
Tying a sacred protective thread around the water tank or key asset, symbolising care and protection
Jal Arpan
Ceremonial offering of water from the newly commissioned source to honour the resource
Pledge Ceremony
Community members collectively promise to maintain and protect the water supply system
Cultural Programmes
Folk songs, street plays, and performances celebrating water security and community achievement
The handover ceremony incorporates traditional and participatory elements to strengthen community bonds and commitment:

## Slide 17
Thank You