## Slide 1
Collectors’ Peyjal Samvad
District - Dhar
Madhya Pradesh Jal Nigam

## Slide 2
Progress since launch of Jal Jeevan Mission in District Dhar
 | More than 75%
 | 51 to 75%
 | 26 to 50%
 | 11 to 25%
 | 0 to 10%
As on 15.08.2019
As on 04.12.2025
2
Progress – 79%
More than 79% rural families in the district are getting tap water.

## Slide 3
District Dhar – Progress under Jal Jeevan Mission
S.No. | Block Name | Total Rural household | Household Connections at Launch of Mission | Total Household connections | Progress (%age) | Nos. of Villages | Nos. of Villages with (100% FHTC) | Progress (%age)
1 | Kukshi | 18,627 | 3,135 | 18,537 | 100% | 48 | 45 | 94%
2 | Nisarpur | 17,948 | 3,423 | 16,903 | 94% | 58 | 42 | 72%
3 | Badnawar | 46,330 | 8,766 | 42,644 | 92% | 165 | 106 | 64%
4 | Dhar | 25,506 | 3,778 | 23,112 | 91% | 98 | 76 | 78%
5 | Gandhwani | 28,012 | 1,864 | 22,921 | 82% | 145 | 82 | 57%
6 | Sardarpur | 61,223 | 6,436 | 49,361 | 81% | 192 | 101 | 53%
7 | Dahi | 19,229 | 1,175 | 15,483 | 81% | 62 | 44 | 71%
8 | Manawar | 30,104 | 3,932 | 22,950 | 76% | 95 | 47 | 49%
9 | Bagh | 21,619 | 169 | 16,406 | 76% | 90 | 47 | 52%
10 | Dharampuri | 32,465 | 6,450 | 23,104 | 71% | 97 | 55 | 57%
11 | Umarban | 33,500 | 3,773 | 22,336 | 67% | 103 | 52 | 50%
12 | Tirla | 19,792 | 2,802 | 11,916 | 60% | 144 | 52 | 36%
13 | Nalchha | 29,580 | 5,357 | 17,699 | 60% | 178 | 65 | 37%
 | Total | 3,83,935 | 51,060 | 3,03,372 | 79% | 1,475 | 814 | 55%

## Slide 4
District Dhar – Success Story

## Slide 5
Scheme Area – District Dhar

## Slide 6
S. No. | Scheme Name | AA Cost (Rs Cr.) | Work Order Date | Name of Contractor | Physical Progress | Scheduled Completion | Expected / Actual Completion
1 | Rajond | 109.50 | 23.12.2021 | LCC Ahmedabad | Completed | 22.12.2023 | 01.07.2024
2 | Mann Dam | 384.05 | 29.03.2023 | WPIL ltd. Kolkata | 59% | 28.03.2025 | 22.03.2026
3 | Bagh | 69.32 | 15.03.2024 | KKCPL Surat | 99% | 15.03.2025 | 31.01.2026
4 | Rignod | 66.89 | 15.03.2024 | KKCPL Surat | 99% | 15.03.2025 | 31.01.2026
5 | Upper Narmada | 1144.00 | 05.09.2023 | DRAIPL Mumbai | 73% | 26.09.2025 | 26.09.2026
6 | Mahi | 2017.92 | 29.09.2023 | Megha Engineering, Hyderabad | 62% | 28.09.2025 | 28.09.2026
7 | Lower Narmada | 302.60 | 29.03.2023 | WPIL ltd. Kolkata | 46% | 28.03.2025 | 22.03.2026
District Dhar- Summary of Major MVS Projects
Back

## Slide 7
Benefits of 24x7 Village Water Supply Initiative
Continuous access to clean water reduces the incidence of waterborne diseases, promoting better health and hygiene practices among villagers.
Access to water at any time improves the overall quality of life, providing convenience for daily activities such as cooking, cleaning, and bathing.
A 24x7 water supply eliminates the need for long trips to fetch water, allowing villagers, especially women and children, to allocate their time to education and income-generating activities.
With less time spent on water collection, children can attend school more regularly, leading to better educational outcomes and future opportunities.
Involving the community in the management and maintenance of water supply systems fosters a sense of ownership and responsibility, empowering villagers to take charge of their resources.

## Slide 8
Model Agreement with Village for 24x7 Water Supply

## Slide 9
Roles and Responsibilities of Gram Panchayats
Preparation and implementation of a water distribution schedule for different hamlets/settlements in the village based on population.
Ensuring proper operation of the main distribution and sluice valves to maintain equitable water supply with adequate pressure across all habitations.
Timely payment of bulk water charges to Jal Nigam as per notified rates and meter readings.
Appointment of a valve operator for operating distribution and sluice valves and ensuring security and protection of all infrastructure within the village boundary, including FHTCs, distribution systems, OHTs, bulk flow meters, and sluice valves.
Fixation of household water charges, periodic revision if required, collection of user charges, and provision of concessions for weaker sections.
Extending cooperation to Jal Nigam in cases where damages to water supply infrastructure are caused by other departments/agencies/persons, to facilitate necessary repairs.

## Slide 10
Gazette Notification of Panchayat and Rural Development
S.No. | Type of Connection | Water Tax (Monthly)
1 | Domestic | Min ₹ 60
2 | Govt Institutions Connection | Min ₹ 200 / Connection
 |  | Min ₹5/KL under Bulk Water Meter Service
3 | Private Institutions Connection | Min ₹ 300 / Connection
4 | Commercial Connection | Min ₹ 500 / Connection
5 | Industrial Connection | Min ₹ 1,000 / Connection or through Bulk Water Meter Service
 |  | Min ₹20/KL under Bulk Water Meter Service
मध्य प्रदेश ग्राम पंचायत (ग्रामीण जल प्रदाय योजना क्रियान्वयन एवं प्रबंधन) नियम, 2020, दिनांक 26.09.2020

## Slide 11
Panchayat Darpan Portal – Bulk Water Charges from GPs
MPJN is using Panchayat Darpan Portal (PDP) for Bulk Water Bill generation and collection from Gram Panchayat/VWSC, with the help of NIC, Bhopal.
To efficiently/effectively monitor Bulk Water Bill generation and collection for Gram Panchayat/VWSC
To automatically generate computerized bills for Gram Panchayat/VWSC
Progress of Bulk Water Bill Generation and collection can be monitored online

## Slide 12
Panchayat Darpan Portal – Bulk Water Charges from GPs
District wise Reports are Generated and pending bills with Payment details.
Particulars | Overall Amount (In Cr.) | Amount Collected in Dhar (In Cr.)
Bill Amount | 117.30 | 2.35
Collection Amount | 12.31 | 0.01
Balance Amount | 104.99 | 2.34
Chart: Monthly Bill / Collection (INR in Cr.)
| 45536 | 45566 | 45597 | 45627 | 45658 | 45689 | 45717 | 45748 | 45778 | 45809 | 45839 | 45870 | 45901 | 45931
Bill | 4.1921 | 3.2993 | 3.8895 | 3.601 | 3.527 | 3.9611 | 4.7141 | 4.39 | 4.3549 | 4.7676 | 4.7568 | 4.5228 | 5.3005 | 4.94
Collection | 0.25602 | 0.27485 | 0.17567 | 0.13625 | 0.21734 | 0.18536 | 0.30835 | 0.32911 | 0.20534 | 0.15599 | 0.3975 | 0.19541 | 0.20953 | 0.0922

## Slide 13
Panchayat Darpan Portal – Bulk Water Charges from GPs
Sample Bill of Rajond MVS for Gram Panchayat Nandlai, Janpad – Sardarpur, District - Dhar
Payment receipt of Rajomd MVS for Gram Panchayat Rajond, District - Dhar

## Slide 14
Challenges after implementation of PDP 2.0
Limited awareness of the digital platform developed by Jal Nigam on PDP among Gram Panchayats (GPs), VWSCs, and general users.
Low willingness and motivation among GPs to make timely Bulk Water payments.
Lack of effective coordination between Gram Panchayats and VWSCs in managing Bulk Water supply and payments.
Limited digital literacy among Panchayat Secretaries, Sarpanches, and field-level functionaries.
Poor internet connectivity in remote and rural areas hampers smooth platform usage.

## Slide 15
Panchayat Darpan Portal – Water User Charges from Citizens
Benefits of UNIPAY in PDP:
Beneficiaries can make payments online anytime and anywhere, instead of visiting Gram Panchayat offices physically.
Eliminates the need for manual payment collection, reducing administrative workload and saving operational costs for Gram Panchayats.
Digitization minimizes cash handling and associated risks, ensuring the full collection of water charges without losses.
Gram Panchayats can access real-time data on collections and allocation for water supply operations and maintenance.
Citizens can search their bills by using Samagra ID, Bill No. and Mobile Number.
Payments can be made by using UNIPAY (through MPSEDC) Payment gateway with help of NEFT/RTGS, UPI/BHIM, Internet Banking, Credit/ Debit Card, Cash Card and IMPS etc.

## Slide 16
Beneficiaries Photographs

## Slide 17
Beneficiaries Photographs

## Slide 18
Thank You

## Slide 19
Contractor: LCC, Ahmedabad |  | 
Schedule Start Date : 13-01-2021 |  | 
Scheduled Completion Date : 12-01-2023 |  | 
Date of Completion : 16-11-2024 |  | 
AA Cost (Rs Cr) : 109.50 |  | 
Agreement Cost (Rs Cr) : 84.41 |  | 
Blocks: Badnawar (40),Sardarpur (39) Total: 79 |  | 
Physical Progress : Completed |  | 
Financial Progress : Completed |  | 
Component | Approved | Executed
Intake Well (15.90 MLD) | 1 nos. | 100%
RWPM | 2.01 km | 100%
WTP (12.51 MLD) | 1 nos. | 100%
CWPM | 149.47 km | 100%
CWGM | 0 | N.A.
OHSR's | 33 nos. | 100%
Distribution | 465.60 km | 100%
Road Restoration | 91.17 km | 100%
HGJ | 74 nos. | 13 nos.
Water Supply Started Villages : 79 |  | 
Rajond MVS : Map
Back
Details

## Slide 20
Rajond MVS : Photograph
Back

## Slide 21
Maan Dam MVS : Map
Contractor: WPIL Ltd., Kolkata |  | 
Schedule Start Date : 23-03-2023 |  | 
Scheduled Completion Date : 22-03-2025 |  | 
Expected Date of Completion : 22-03-2026 |  | 
AA Cost (Rs Cr) : 384.05 |  | 
Agreement Cost (Rs Cr) : 291.93 |  | 
Blocks: Bagh (4), Dhar(26), Gandhwani (42), Nalchha (24), Sardarpur (46), Tirla (52) Total: 194 |  | 
Physical Progress : 58.85% |  | 
Financial Progress : 55.00% |  | 
Component | Approved | %age
Intake Well (37.20 MLD) | 1 nos. | 80%
RWPM | 3.27 km | 79.47%
WTP (27.42 MLD) | 1 nos. | 54.45%
CWPM | 58.70 km | 58.22%
OHSR's | 57 nos. | 14.91%
Distribution | 465.77 km | 64.71%
Road Restoration | 1.6 km | 10%
HGJ | - | -
Water Supply Started Villages : NIL |  | 
Details
Back

## Slide 22
Maan Dam MVS : Photograph
Intake well
Filter House
Back

## Slide 23
Lower Narmada MVS : Map
Contractor: WPIL Ltd., Kolkata |  | 
Schedule Start Date : 23-03-2023 |  | 
Scheduled Completion Date : 22-03-2025 |  | 
Expected Date of Completion : 22-03-2026 |  | 
AA Cost (Rs Cr) : 302.60 |  | 
Agreement Cost (Rs Cr) : 225.86 |  | 
Blocks: Dahi (12), Nisarpur (31), Manawar (22), Umarban (27), Dharampuri(22) Total: 114 |  | 
Physical Progress : 46.15% |  | 
Financial Progress : 39.00% |  | 
Component | Approved | Executed
Intake Well (31.14 MLD) | 1 nos. | 67%
RWPM | 7.70 km | 76.24%
WTP (25.00 MLD) | 1 nos. | 50.75%
CWPM | 274.46 km | 53.52%
CWGM | 0 | N.A.
OHSR's | 42 nos. | 12.38%
Distribution | 669.67 km | 51.05%
Road Restoration | 11.90 km | 10%
HGJ | - | -
Water Supply Started Villages : NIL |  | 
Details
Back

## Slide 24
Lower Narmada MVS : Photograph
Intake well
Aerator
Back

## Slide 25
Narmada River Part B (Upper Narmada) MVS : Map
Contractor: Dineshchandra R Agrawal Infracon, Ahmedabad |  | 
Schedule Start Date : 26-09-2023 |  | 
Scheduled Completion Date : 25-09-2025 |  | 
Expected Date of Completion : 25-09-2026 |  | 
AA Cost (Rs Cr) : 1,144.49 |  | 
Agreement Cost (Rs Cr) : 1,044.00 |  | 
Blocks: Bagh (19), Dahi (48), Dharampuri (75), Gandhwani (102), Kukshi (31), Manawar (71), Nalchha (157), Nisarpur (23), Tirla (71), Umarban (76), Total: 673 |  | 
Physical Progress : 72.95% |  | 
Financial Progress : 64.39% |  | 
Component | Approved | Executed
Intake Well (134.03 MLD) | 1 nos. | 59.80%
RWPM | 8.33 km | 87.975
WTP (103.20 MLD) | 1 nos. | 45.30%
CWPM | 1205 km | 86.40%
OHSR's | 192 nos. | 19.79%
Distribution | 1307 km | 67.96%
Road Restoration | 45.63 km | 42.65%
HGJ | - | -
Water Supply Started Villages : NIL |  | 
Details
Back

## Slide 26
Narmada River Part B (Upper Narmada) MVS : Photograph
Intake well
PST and PST Sludge sump
Back

## Slide 27
Baagh MVS : Map
Contractor: Keshav Krupa Construction Pvt. Ltd., Surat |  | 
Schedule Start Date : 06-04-2024 |  | 
Scheduled Completion Date : 06-04-2025 |  | 
Expected Date of Completion : 04-10-2025 |  | 
AA Cost (Rs Cr) : 69.32 |  | 
Agreement Cost (Rs Cr) : 60.61 |  | 
Blocks: Bagh (26), Kukshi (3) Total: 29 |  | 
Physical Progress : 99.72% |  | 
Financial Progress : 91.29% |  | 
Component | Approved | Executed
Intake Well (7.20 MLD) | 1 nos. | 100%
RWPM | 0.26 km | 100%
WTP (6.00 MLD) | 1 nos. | 100%
CWPM | 10.55 km | 64.93%
CWGM | 44.63 km | 91.71%
OHSR's | 10 nos. | 100%
Distribution | 363.40 | 100%
Road Restoration | 10 km | 100%
HGJ |  | -
Water Supply Started Villages : 29 |  | 
Details
Back

## Slide 28
Baagh MVS : Photograph
Intake well
WTP
Back

## Slide 29
Contractor: Keshav Krupa Construction Pvt.Ltd., Surat |  | 
Schedule Start Date : 05-04-2024 |  | 
Scheduled Completion Date : 04-04-2025 |  | 
Expected Date of Completion : 04-10-2025 |  | 
AA Cost (Rs Cr) : 66.90 |  | 
Agreement Cost (Rs Cr) : 51.63 |  | 
Blocks: Sardarpur(37) Total: 37 |  | 
Physical Progress : 99.27%% |  | 
Financial Progress : 91.00% |  | 
Component | Approved | Executed
Intake Well (11.92 MLD) | 1 nos. | 100%
RWPM | 2.77 km | 100%
WTP (9.65 MLD) | 1 nos. | 100%
CWPM | 50.94 km | 100%
CWGM | 18.06 km | 100%
OHSR's | 17 nos. | 100%
Distribution | 216.14 km | 100%
Road Restoration | 50.46 km | 100%
HGJ | - | -
Water Supply Started Villages : 37 |  | 
Rignod MVS : Map
Details
Back

## Slide 30
Rignod MVS : Photograph
Intake well
WTP
Back

## Slide 31
Mahi MVS : Map
Contractor: Megha, Hyderabad |  | 
Schedule Start Date : 29-09-2023 |  | 
Scheduled Completion Date : 28-09-2025 |  | 
Expected Date of Completion : 28-09-2026 |  | 
AA Cost (Rs Cr) : 2,017.92 |  | 
Agreement Cost (Rs Cr) : 1,719.00 |  | 
Blocks: Badnawar (117), Bajna (27), Dhar (11), Jaora (145), Piploda (88), Ratlam (152), Sailana (219), Sardarpur (30) Total: 789 |  | 
Physical Progress : : 61.91% |  | 
Financial Progress : 46.75% |  | 
Component | Approved | Executed
Intake Well (209.07 MLD) | 1 nos. | 15.50%
RWPM | 1.01 km | 10%
WTP (164.62 MLD) | 1 nos. | 15.76%
CWPM | 418.67 km | 50.86%
CWGM | 1711.25km | 67.66%
OHSR's | 277nos. | 18.07%
Distribution | 1935.37km | 67.87%
Road Restoration | 0 km | N.A.
HGJ | - | -
Water Supply Started Villages : NIL |  | 
Details
Back

## Slide 32
Mahi MVS : Photograph
CLF
Intake Well
Back

## Slide 33
Baagh MVS : Basic Details (Balance Works)
S. No. | Particulars |  | Details
1 | District |  | Dhar
2 | AA Cost (Rs. Cr.) |  | 69.32
3 | Villages Covered |  | 29
4 | Households |  | 8,604
5 | Name of Contractor |  | Keshav Krupa Construction Pvt.Ltd., Surat
6 | Agreement Cost (Rs. Cr.) |  | 60.61
7 | Revised Cost (Rs. Cr. with Variation) |  | -
8 | Overall Physical Progress (%) | Expected | 100%
 |  | Current | 98.72%
9 | Overall Financial Progress (%) |  | 94.03%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 56.99
11 | Schedule Start Date |  | 06-04-2024
12 | Scheduled Completion Date (Duration) |  | 06-04-2025 (12 Months)
13 | Expected Date of Completion |  | 04-10-2025
14 | Issues |  | -
Back

## Slide 34
Baagh MVS – Physical Progress (Balance Works)
S. No. | Activities as per approved construction program | Unit | Approved Quantity
1 | WTP (E&M Works & SCADA) | Nos. | 1
2 | CWPM | Km | 7.51
3 | CWGM | Km | 40.83
4 | Raw Water Pumps | Nos. | 0
5 | Clear Water Pumps | Nos. | 0
6 | Distribution Network | Km | 131.65
7 | SCADA | Nos. | 1
8 | HSC | Nos. | 3,597
9 | Road Restoration | Km | 10
*Minor Works are in Intake Well, RWPM, Overhead Tanks and Powerline & Substations
Back

## Slide 35
Baagh MVS : Basic Details (Old Contract)
S. No. | Particulars |  | Details
1 | District |  | Dhar
2 | AA Cost (Rs. Cr.) |  | 69.32
3 | Villages Covered |  | 29
4 | Households |  | 10,104
5 | Name of Contractor |  | M/s Technodrillers - Sarbha – Satpura - JV
6 | Agreement Cost (Rs. Cr.) |  | 45.53
7 | Revised Cost (Rs. Cr. with Variation) |  | 55.54
8 | Overall Physical Progress (%) | Expected | 100%
 |  | Current | 88%
9 | Overall Financial Progress (%) |  | 83%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 45.78
11 | Schedule Start Date |  | 09-05-2017
12 | Scheduled Completion Date (Duration) |  | 08-11-2018 (18 Months)
13 | Expected Date of Completion |  | Contract Terminated on Dated : 12-12-2023
14 | Issues |  | -
Back

## Slide 36
Baagh MVS – Physical Progress (Old Contract)
S. No. | Activities as per approved construction program | Unit | Approved Quantity | Executed Quantity | % age
1 | Intake well (7.2 MLD) (Source - Thana Dam) | Nos. | 1 | 1 | 100
2 | RWPM | Km | 0.30 | 0.30 | 100
3 | WTP (6.0 MLD) | Nos. | 1 | 1 | 98
4 | CWPM | Km | 8 | 0.02 | 0.01
5 | CWGM | Km | 41 | 41 | 100
6 | Overhead Tanks | Nos. | 10 | 10 | 99
7 | Raw Water Pumps | Nos. | 2 | 2 | 100
8 | MBR | Nos. | 1 | 1 | 100
9 | Clear Water Pumps | Nos. | 2 | 2 | 100
10 | Power line and substation (13.525km) | Km / Nos | 1 | 1 | 100
11 | Distribution Network | Km | 303 | 231 | 76
12 | SCADA | Nos. | 1 | - | -
13 | HSC | Nos. | 10,104 | 5,007 | 50
14 | Road Restoration | Km | 10 | 10 | 100
15 | Overall Physical Progress |  |  |  | 88%
Back

## Slide 37
Rignod MVS : Basic Details (Balance Works)
S. No. | Particulars |  | Details
1 | District |  | Dhar
2 | AA Cost (Rs. Cr.) |  | 66.90
3 | Villages Covered |  | 37
4 | Households |  | 12,961
5 | Name of Contractor |  | Keshav Krupa Construction Pvt.Ltd., Surat
6 | Agreement Cost (Rs. Cr.) |  | 51.63
7 | Revised Cost (Rs. Cr. with Variation) |  | -
8 | Overall Physical Progress (%) | Expected | 100%
 |  | Current | 98.44%
9 | Overall Financial Progress (%) |  | 94.87%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 76.41
11 | Schedule Start Date |  | 05-04-2024
12 | Scheduled Completion Date (Duration) |  | 04-04-2025 (12 Months)
13 | Expected Date of Completion |  | 04-10-2025
14 | Issues |  | MPRRDA – 1
Back

## Slide 38
Rignod MVS– Physical Progress (Balance Works)
S. No. | Activities as per approved construction program | Unit | Approved Quantity
1 | RWPM | Km | 0.14
2 | CWPM | Km | 48.70
3 | Intermediate Pumping Stations | Nos. | 2
4 | CWGM | Km | 15.96
5 | Raw Water Pumps | Nos. | 1
6 | Clear Water Pumps | Nos. | 1
7 | Overhead Tanks | Nos. | 17
8 | Distribution Network | Km | 189.03
9 | Power line and substation | Km | 36.48
10 | SCADA | Nos. | 1
11 | HSC | Nos. | 12961
12 | Road Restoration | Km | 50.50
*Minor Works are in Intake Well and WTP
Back

## Slide 39
Rajond MVS : Basic Details
S. No. | Particulars | Details
1 | District | Dhar
2 | AA Cost (Rs. Cr.) | 109.50
3 | Villages Covered | 79
4 | Households | 25,559
5 | Name of Contractor | LCC Projects Pvt. Ltd., Ahmedabad
6 | Agreement Cost (Rs. Cr.) | 84.41
7 | Revised Cost (Rs. Cr. with Variation) | 91.97
8 | Expenditure Incurred (Rs. Cr.) (incl. advance) | 88.05
9 | Schedule Start Date | 13-01-2021
10 | Scheduled Completion Date (Duration) | 12-01-2023 (24 Months)
11 | Date of Completion | 16-11-2024
12 | Water Supply Date | 01-07-2024
13 | Issues | -
Back

## Slide 40
Rajond MVS – Physical Progress
S. No. | Activities as per approved construction program | Unit | Approved Quantity | Executed Quantity
1 | Intake well (15.9 MLD) (Source: Mahi Dam) | Nos. | 1 | 1
2 | Raw Water Pumping Main | KM | 2 | 2
3 | WTP ( 12.51 MLD) | Nos. | 1 | 1
4 | Clear Water Pumping Main | KM | 149 | 149
5 | Intermediate Pumping Station | Nos. | 1 | 1
6 | Refurbishing existing OHTs | Nos. | 13 | 13
7 | Overhead Tanks | Nos. | 33 | 33
8 | Distribution Network | KM | 529 | 529
9 | Raw Water Pump | Nos. | 4 | 4
10 | Clear Water Pump | Nos. | 8 | 8
11 | Power line & Sub Station | KM/Nos. | 16 | 16
12 | SCADA | Nos. | 1 | 1
13 | House service Connections | Nos. | 25,559 | 24,767
14 | Road Restoration | KM | 91 | 90
Back

## Slide 41
Maan Dam MVS : Basic Details
S. No. | Particulars |  | Details
1 | District |  | Dhar
2 | AA Cost (Rs. Cr.) |  | 384.05
3 | Villages Covered |  | 194
4 | Households |  | 38,184
5 | Name of Contractor |  | WPIL Ltd., Kolkata
6 | Agreement Cost (Rs. Cr.) |  | 291.93
7 | Revised Cost (Rs. Cr. with Variation) |  | 283.24
8 | Overall Physical Progress (%) | Expected | 66%
 |  | Current | 58.37%
9 | Overall Financial Progress (%) |  | 55.49%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 157.16 Cr.
11 | Schedule Start Date |  | 23-03-2023
12 | Scheduled Completion Date (Duration) |  | 22-03-2025 (24 Months)
13 | Expected Date of Completion |  | 22-03-2026
14 | Issues |  | Forest-1, Railway-1, NHAI-1, MPRDC-1, PWD-1, MPRRDA-2, NVDA-2, GAIL-1
Back

## Slide 42
Maan Dam MVS – Physical Progress
S. No. | Activities as per approved construction program | Unit | Approved Quantity | Executed Quantity | % age
1 | Intake well(37.2 MLD) (Source - Maan Dam) | Nos | 1.00 | - | 74.00
2 | Raw Water Pumping Main | KM | 3.27 | 3.10 | 79.47
3 | Water Treatment Plant 27.42 MLD | Nos | 1.00 | - | 51.55
4 | Clear Water Pumping Main | KM | 58.70 | 21.23 | 58.22
5 | Clear Water Gravity Main | KM | 420.63 | 206.16 | 74.92
6 | Oht + Gsr | Nos | 57.00 | 10.00 | 11.75
7 | Clear Water Sump Cum Pump House | Nos | 1.00 | - | 5.00
8 | Master Balancing Reservoir | Nos | 2.00 | - | 15.00
9 | Distribution Network | KM | 465.77 | 224.31 | 64.62
10 | Raw Water Pumping Machinary | Nos | 4.00 | 4.00 | 65.00
11 | Clear Water Pumping Machinary | Nos | 20.00 | 8.00 | 29.00
12 | Power Line & Substation | KM | 53.00 | - | 2.50
13 | Scada System | Nos | 1.00 | - | 5.00
14 | House Service Connection | Nos | 38184.00 | - | -
15 | Staff Quarters | Nos | 13.00 | 3.00 | 13.08
16 | Road Restoration | KM | 1.00 | - | -
 | Overall Physical Progress |  |  |  | 58.37
Back

## Slide 43
Lower Narmada MVS : Basic Details
S. No. | Particulars |  | Details
1 | District |  | Dhar
2 | AA Cost (Rs. Cr.) |  | 302.60
3 | Villages Covered |  | 114
4 | Households |  | 30,479
5 | Name of Contractor |  | WPIL Ltd., Kolkata
6 | Agreement Cost (Rs. Cr.) |  | 225.86
7 | Revised Cost (Rs. Cr. with Variation) |  | 190.17
8 | Overall Physical Progress (%) | Expected | 66%
 |  | Current | 45.38%
9 | Overall Financial Progress (%) |  | 43.71%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 83.13
11 | Schedule Start Date |  | 23-03-2023
12 | Scheduled Completion Date (Duration) |  | 22-03-2025 (24 Months)
13 | Expected Date of Completion |  | 22-03-2026
14 | Issues |  | Forest-1, NHAI-1, MPRDC-2, PWD-2, MPRRDA-1, NVDA-1, BPCL-1
Back

## Slide 44
Lower Narmada MVS – Physical Progress
S. No. | Activities as per approved construction program | Unit | Approved Quantity | Executed Quantity | % age
1 | Intake well (31.14 MLD) (Source - Narmada River) | Nos | 1.00 | - | 65.00
2 | Raw Water Pumping Main | KM | 7.70 | 4.26 | 74.62
3 | Water Treatment Plant 25.0 MLD | Nos | 1.00 | - | 46.45
4 | Clear Water Pumping Main | KM | 274.46 | 88.60 | 53.14
5 | Clear Water Gravity Main | KM | - | - | -
6 | Oht + Gsr | Nos | 42.00 | 4.00 | 10.95
7 | Clear Water Sump Cum Pump House | Nos | 1.00 | - | -
8 | Master Balancing Reservoir | Nos | - | - | -
9 | Distribution Network | KM | 669.67 | 195.16 | 50.50
10 | Raw Water Pumping Machinary | Nos | 4.00 | - | 65.00
11 | Clear Water Pumping Machinary | Nos | 24.00 | - | 25.00
12 | Power Line & Substation | KM | 28.50 | - | 2.50
13 | Scada System | Nos | 1.00 | - | 5.00
14 | House Service Connection | Nos | 30479.00 | - | -
15 | Staff Quarters | Nos | 6.00 | - | 6.67
16 | Road Restoration | KM | 8.96 | - | -
 | Overall Physical Progress |  |  |  | 45.38
Back

## Slide 45
Mahi MVS : Basic Details
S. No. | Particulars |  | Details
1 | District |  | Ratlam & Dhar
2 | AA Cost (Rs. Cr.) |  | 2,017.92
3 | Villages Covered |  | 804
4 | Households |  | 2,12,450
5 | Name of Contractor |  | M/s Megha, Hyderabad
6 | Agreement Cost (Rs. Cr.) |  | 1,719.00
7 | Revised Cost (Rs. Cr. with Variation) |  | 1,453.72
8 | Overall Physical Progress (%) | Expected | 29%
 |  | Current | 46.39%
9 | Overall Financial Progress (%) |  | 25.48%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 370.42
11 | Schedule Start Date |  | 29-09-2023
12 | Scheduled Completion Date (Duration) |  | 28-09-2025 (24 Months)
13 | Expected Date of Completion |  | 28-09-2026
14 | Issues |  | Forest-1, PWD-2, MPRRDA-3
Back

## Slide 46
Mahi MVS – Physical Progress
S. No. | Activities as per approved construction program | Unit | Approved Quantity | Executed Quantity | % age
1 | Intake well Cum pump house (209.07 MLD) (Source - Talawada Barrage) | Nos | 1 | - | 15.5
2 | Raw Water Pumping Main | KM | 1.01 | - | 10.0
3 | Water Treatment Plant 164.62 MLD | Nos | 1 | - | 15.7
4 | Clear Water Pumping Main | KM | 418.67 | 2 | 39.6
5 | Clear Water Gravity Main | KM | 1711.25 | 215 | 61.3
6 | OHT + GSR | Nos | 277 | 123 | 12.2
7 | Clear Water Sump Cum Pump House | Nos | 15 | - | 4.0
8 | Master Balancing Reservoir | Nos | 6 | - | 10.0
9 | Distribution Network | KM | 1935.37 | 752 | 67.7
10 | Raw Water Pumping Machinary | Nos | 4 | - | -
11 | Clear Water Pumping Machinary | Nos | 27 | - | -
12 | Power Line & Substation | KM | 57 | - | -
13 | Scada System | Nos | 1 | - | -
14 | House Service Connection | Nos | 212450 | - | -
15 | Staff Quarters | Nos | 26 | - | 5.0
16 | Road Restoration | KM | 40 | 38 | -
 | Overall Physical Progress |  |  |  | 45.22
Back

## Slide 47
Narmada River Part B (Upper Narmada) MVS : Basic Details
S. No. | Particulars |  | Details
1 | District |  | Dhar
2 | AA Cost (Rs. Cr.) |  | 1,144.49
3 | Villages Covered |  | 673
4 | Households |  | 76,106
5 | Name of Contractor |  | Dineshchandra R Agrawal Infracon Pvt Ltd, Ahmedabad
6 | Agreement Cost (Rs. Cr.) |  | 1,044.00
7 | Revised Cost (Rs. Cr. with Variation) |  | 999.73
8 | Overall Physical Progress (%) | Expected | 31%
 |  | Current | 71.10%
9 | Overall Financial Progress (%) |  | 68.36%
10 | Expenditure Incurred (Rs. Cr.) (incl. advance) |  | 683.40
11 | Schedule Start Date |  | 26-09-2023
12 | Scheduled Completion Date (Duration) |  | 25-09-2025 (24 Months)
13 | Expected Date of Completion |  | 25-09-2026
14 | Issues |  | Forest-2, NHAI-1, PWD-NH-1, MPRDC-14, PWD-2, Others-2
Back

## Slide 48
Narmada River Part B (Upper Narmada) MVS – Physical Progress
S. No. | Activities as per approved construction program | Unit | Approved Quantity | Executed Quantity | % age
1 | Intake well (134.03 MLD) (Source - Narmada River) | Nos. | 1.00 | - | 58.40
2 | Raw Water Pumping Main | KM | 8.33 | 6.42 | 87.84
3 | Water Treatment Plant (103.20 MLD) | Nos. | 1.00 | - | 44.80
4 | Clear Water Pumping Main | KM | 1205.43 | 766.50 | 85.71
5 | Clear Water Gravity Main | KM | 437.21 | 273.80 | 80.90
6 | Overhead Tanks | Nos. | 192.00 | 59.00 | 16.88
7 | Master Balancing Reservoir | Nos. | 2.00 | 2.00 | 20.00
8 | Clear Water Sump Cum pump House | Nos. | 20.00 | 2.00 | 6.00
9 | Raw Water Pumps | Nos. | 4.00 | - | -
10 | Clear Water Pumps | Nos. | 54.00 | - | -
11 | Power line and substation | KM/ | 174.5 / 21 | - | -
12 | SCADA | Nos | 1.00 | - | -
13 | Distribution Network | Nos. | 1338.81 | 759.00 | 67.43
14 | House Service Connections | KM | 76106.00 | 4850.00 | 4.46
15 | Staff Quarters (F-1,G-2,H-4,I-12) Nos | Nos. | 19.00 | - | 13.16
16 | Road Restoration | Nos. | 43.80 | 7.70 | 14.00
 | Overall Physical Progress |  |  |  | 71.10
Back