## Slide 1: COLLECTOR’S PEYJAL SAMVAD District– Shahjahanpur(U.P.) Date-(11/12/2025)
Best Practices • Community Participation • JJM Innovations

## Slide 2: JJM Physical Progress – Shahjahanpur
Chart: 
| Tubewell (867/866 No’s) | Pump House (867/858 No’s) | Solar System (830/829 No’s) | Over Head Tank (861/379 No’s) | Distribution Line (9291/9177 km) | Road Restoration (7198/7123 km) | FHTC Coverage (447768/445780 No’s) | Chlorinator System (867/755 No’s) | Scada Automation (867/755 No’s) | Regular water supply (2024/1589 villages) | Har Ghar Jal certification (865/313 Schemes) | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Percentage (%) | 99.654 | 98.9619 | 99.8795 | 44.0186 | 98.773 | 98.958 | 99.556 | 87.0819 | 87.0819 | 78.5079 | 36.185

## Slide 3: JJM Schemes

## Slide 4: "APNI CHAUPAL" (chaupal.shahjahanpur.up.in) (New Initiative by District Shahjahanpur)

## Slide 5: Main Features
Every Friday
65 Villages
One District Level Officer
Discussions & Inspection with Villagers
All Village Level Employees

## Slide 6: Department Reviewed
.
1 | Revenue Department
2 | Rural Development Department
3 | Education Department
4 | Health Department
5 | Animal Husbandry Department
6 | Panchayti Raj Department
7 | Social Welfare Department
8 | Jal Jeevan Mission
9 | Other Concerned Departments

## Slide 7: JJM IN APNI CHAUPAL
Inspection of works: Quality, functionality, and compliance of JJM assets verified on-site.
Door to door visit: Household-level check of FHTC, supply regularity, and pressure status.
Feedback and complaints: Collection of issues and immediate redressal for service improvement.

## Slide 8: COMPLAINT TYPES JJM
Chart: 
| REGULAR WATER SUPPLY | FHTC CONNECTION | PIPELINE LAYING | ROAD RESTORATION | LEAKAGE | OHT WORK NOT COMPLETED | HANDPUMP DEMAND | 1 | 2 | 3 | 4 | 5 | 5 | 6
RECEIVED | 50 | 115 | 28 | 54 | 29 | 3 | 8
RESOLVED | 42 | 111 | 23 | 51 | 27 | 1 | 0
TOTAL COMPLAINT RECEIVED-287
TOTAL COMPLAINT RESOLVED-255

## Slide 9: IMPACT OF JAN CHAUPAL ON JJM
Jan Chaupal
​ System gaps identified
​ O&M practices strengthened
​ Grievances and feedback addressed
​ Water quality & pressure verified
Har Ghar Jal certification
Scheme operationally ready
Jal Arpan (formal handover & community ownership)
Improvement in Jan Bhagidari and sense of ownership

## Slide 10: APNI CHAUPAL

## Slide 11: IMPLEMENTATION SUPPORT AGENCY (ISA) ACTIVITIES

## Slide 12: IMPLEMENTATION SUPPORT AGENCY (ISA) ACTIVITIES

## Slide 13: INFORMATION, EDUCATION AND COMMUNICATION (IEC) ACTIVITIES

## Slide 14: INFORMATION, EDUCATION AND COMMUNICATION (IEC) ACTIVITIES

## Slide 15: Thank You